## Sheet1
| TASK NAME | START DATE | END DATE | DURATION (WORK DAYS) | TEAM MEMBER | PERCENT COMPLETE | Week 1 | [6 empty] | Week 2 | [6 empty] | Week 3 | [6 empty] | Week 4 | [6 empty] | Week 5
[7 empty] | M | Tu | W | Th | F | Sa | Su | M | Tu | W | Th | F | Sa | Su | M | Tu | W | Th | F | Sa | Su | M | Tu | W | Th | F | Sa | Su | M | Tu | W | Th | F | Sa | Su
First sprint | bar: Week 1 M; Week 1 Sa; Week 2 Th; Week 3 Tu; Week 3 Su; Week 4 F; Week 5 W
| Creating initial Gantt chart | 2020-01-28 | 2020-02-03 | 5 | Ben | 100% | bar: Week 1 Tu to Week 2 M
| Approving Gantt chart | 2020-02-03 | 2020-02-06 | 4 | Team | 100% | bar: Week 2 M to Week 2 Th
| Requirement Analysis | 2020-01-28 | 2020-02-03 | 5 | Ben and Joe L. | 100% | bar: Week 2 F to Week 3 M
| Approval of requirements analysis | 2020-02-03 | 2020-02-06 | 4 | Team | 100% | bar: Week 3 M
| Risk analysis | 2020-02-03 | 2020-02-06 | 4 | Team | 100% | bar: Week 2 M to Week 2 Su
| Success criteria | 2020-02-03 | 2020-02-11 | 7 | Ben and Joe L. | 100% | bar: Week 2 F to Week 2 Sa
| Design | 2020-02-12 | 2020-02-18 | 5 | Joe C. and Joe L. | 100% | bar: Week 3 W to Week 3 Su
| Design Documentation | 2020-02-13 | 2020-02-21 | 7 | Joe L. | 100% | bar: Week 3 Sa to Week 3 Su
| Coding | 2020-02-20 | 2020-03-06 | 12 | Alex, Joe C., Tom | 80% | bar: Week 4 W to Week 5 Su
| Software documentation | 2020-02-24 | 2020-03-06 | 10 | Joe L., Ben, Alex | 70% | bar: Week 4 Sa to Week 5 Su
| Testing | 2020-03-06 | 2020-03-11 | 4 | Team | 70% | bar: Week 4 Sa to Week 5 Su
| Art | 2020-02-08 | 2020-02-14 | 5 | Tom | 100% | bar: Week 4 Tu to Week 5 Su
Formulas:
DURATION (WORK DAYS) = NETWORKDAYS([START DATE],[END DATE])